## Gantt Chart Template
GANTT CHART | [27 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Agario but AI |  |  |  |  | COMPANY NAME | [8 empty] | AI plays games
| PROJECT MANAGER | Calvin |  |  |  |  | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Evan Luo |  |  | 1 week | 100% | bar: WEEK 1 M to WEEK 1 F
1.1.1 | Project Charter Revisions | Calvin Webb |  |  | 1 day | 100% | bar: WEEK 1 F
1.2 | Research | Brannon Lai |  |  | 2 days | 100% | bar: WEEK 1 F to WEEK 2 M
1.3 | Projections | Ethan Mabey |  |  | 2 days | 80% | bar: WEEK 2 T to WEEK 2 W
1.4 | Stakeholders | Kapptie |  |  | 0 | ? | bar: WEEK 2 W
1.5 | Guidelines | Jeffery Zou |  |  | 1 day | 100% | bar: WEEK 2 R
1.6 | Project Initiation | Evan Luo |  |  | 1 day | 100% | bar: WEEK 1 M
2 | Project Definition and Planning
2.1 | Scope & Goal Setting | Jeffery Zou |  |  | 1 week | 50% | bar: WEEK 2 M to WEEK 2 F
2.2 | Plan | Brannon Lai |  |  | 1 week | 30% | bar: WEEK 2 T to WEEK 3 M
2.3 | Communication Plan | Evan Luo |  |  | 5 days | 30% | bar: WEEK 2 R to WEEK 3 W
2.4 | Examples | Calvin Webb |  |  | 2 days | 50% | bar: WEEK 2 M to WEEK 2 T
3 | Project Completion
3.1 | Startscreen | Brannon Lai |  |  | 1 week | 100% | bar: WEEK 4 M to WEEK 4 F
3.2 | Functionality | Calvin Webb |  |  | 3 weeks | 20% | bar: WEEK 4 M to WEEK 6 F
3.2.1 | Food | Evan Luo |  |  | 2 weeks | 40% | bar: WEEK 5 M to WEEK 6 F
3.2.2 | Cells | Ethan Mabey |  |  | 2 weeks | 10% | bar: WEEK 4 M to WEEK 5 F
3.3 | Project Updates | Evan Luo |  |  | 1 week | 20% | bar: WEEK 7 M to WEEK 8 M
3.3.1 | Chart Updates | Jeffery Zou |  |  | 1 week | 10% | bar: WEEK 7 M to WEEK 8 M
4 | Bug Fixing
4.1 | N/A | All |  |  | ? | 0%
4.2 | TBD | All |  |  | ? | 0%
4.3 | Github | All |  |  | ? | 0%
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## Try Smartsheet
Try Smartsheet for Free